## Tracker
Item | Status | Time taken | ETA | Notes
Rename Avni Vercel -> AvniHub (folders, engine, launcher, catalogue, repo) | Done | 20 min | - | 01-09-2026 19:53. DB preserved through rename (submission 1 intact)
Local rail: engine avnihub.py on :8190 (SQLite) | Done | - | - | MEASURED 19:53: /health -> AvniHub 0.1, sites 1, pages 2, submissions 1
Supabase master rail: avnihub_submissions + avnihub-receipts bucket + edge fn | Done | 40 min | - | MEASURED: public POST -> ok id 1&2; RLS ON, anon read = []; receipts in private bucket; project Sehgal Hero ap-south-1
Public page rail: GitHub Pages | Done | 15 min | - | MEASURED: https://sehgalautoriders.github.io/avnihub/ -> 200; page posts to edge fn; CORS verified from github.io origin
GitHub repo sehgalautoriders/avnihub (public) | Done | - | - | main cd44df1 + gh-pages branch; data/ git-ignored, no secrets in repo
ROADMAP.md: all 21 Vercel uses mapped, phases v0.2-v0.6 | Done | - | - | 3 uses HAVE already (static hosting, CLI deploy, form capture - the last one Vercel itself lacks)
Phone-on-same-WiFi (local rail) | Pending | - | 1 click | Ravi: run 'Allow AvniHub on Wi-Fi.cmd' (Desktop) as administrator. NOTE: phones can already use the PUBLIC page instead
Own domain (avnihub.??) | Pending | - | days | Ravi: 'move to our own domain in some days'. Needs domain purchase (Ravi) + DNS + Pages custom domain + cert (auto)
v0.2: versioned deploys + rollback + request logs | Pending | - | next | First build phase
Engine sync SQLite <-> Supabase (one command) | Can be done | - | - | Both rails live; sync closes the loop
WABA template -> our URL | Pending | - | - | Public URL now EXISTS (github.io). Repoint = Meta re-approval; current leg on original Vercel via Antigravity - verify tier is commercial-compliant
Trademark 'Avni' (lawyer) | Cannot do | - | Ravi | Ravi's action with lawyer. Claude can prepare the brief: classes 9+42, ipindia prior-mark search
Avni Store row (AvniHub) | Done | - | - | Catalogue regenerated: 60 products, launcher rebuilt 50,688 B, payload staged
Target: 1 year, 5000 apps, market entry | Pending | - | 01-09-2027 | ~250 GB at 50 MB avg/app; storage pricing due at v0.4; tenant isolation + abuse controls before market